## Sheet1
Risk | Likelihood | Severity | Control Measure | Revisit 06/05/2021 | Revisit 09/05/2021
Not learning Angular well enough to use in developing my project's front-end | Medium | Medium | Request for help and support early. Also pay particular attention to the ASP.NET content could work as a viable alternative | Edsal is still on leave and so I might struggle implement one of my feature. However, my revision from last weekend is helping me proceed at an okay pace. Even without Edsel, likelihood is now a LOW | Angualr didn't prove to be much of a problem coding-wise. Using YouTube videos plus my revision, I was able to implement the features I wanted bar one
Designing sub par views for my webpages | Medium | low | Reach out to more artistic individuals within the chort for support. | Spoke to Keneil, who gave some ideas using MyAnimeList.com as an example. Also used the template .NET's MVC. Starting well so far | Using library likes material design bootstrap for angular has made designing the UI much easier. Likelihood of this risk is now low
Being unable to finish the project within the alloted time (deadline 10th May) | Medium | High | Create a timing plan that helps me pace myself. Ensure the MVP is completed before proceeding to extend the app's functionality | Testing has wrench a wrench in the works. Having to change code implementation last minute to test code. Having to delay updating docs and practicing devops part of the project. Likelihood High | This seems very likely as my deployed apps are not working properly.
Losing my work | Low | High | Frequently push my code to GitHub | Feature branch implementation is working well likelihood still very low | Been implementing my features on feature branches so this is not a problem. Likelihood still very low
Possibly not being able to link my front-end with the back-end when the project is deployed into production | Medium | High | Seek clarity on how this can be achieved from the QA instructors (Edsel, Dara and Ben) | Briefly spoke to Ben about possible solutions to deploying project to production. However much much still needs to be done to gain clarity as to how I should proceed. Likelihood of risk is now High | Cannot link app in Production. The process provided in the tutorial ddoes not apply to my deployment. Should have sought help much earlier. Likelihood of failing HIGH. Will focus on docs now
Issues with deploying my project to an Azure virtual machine | Low | High | Ensure before the day of the submission, I have deployed my project to a virtual machine times. Even though it might be an incomplete project. Targeting 5 times by the 7th of May | not required | not required